## Matthew Robles
To-do list
To be completed by: |  |  |  | Name: Matthew Robles
Deadline: |  |  |  | Date: 5/17/24
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Days | Revision Notes
100% | Planning | 2024-05-13 | 2024-05-15 | 2024-05-15 | 2 Days
100% | Add Foreign Key | 2024-05-13 | 2024-05-15 | 2024-05-15 | 2 Days
100% | Add Room_Locatiom | 2024-05-13 | 2024-05-15 | 2024-05-15 | 2 Days
100% | Testing | 2024-05-13 | 2024-05-15 | 2024-05-15 | 2 Days
100% | Attended Meetings 5/10, 5/12, 5/14/ 5/16 | 2024-05-10 | 2024-05-15 | 2024-05-17 | 5 Days
100% | Recorded and explained groupmates queries | 2024-05-17 | 2024-05-15 | 2024-05-17 | 1 Day
0%
0%
0%

## Faisal Areefin
To-do list
To be completed by: |  | Faisal Areefin |  | Name: Faisal Areefin
Deadline: |  |  |  | Date: 5/17/24
Project 3
Personal Task | Start By | Finish By | Duration | % done | Revision Notes
Reading the specification | 2024-05-08 | 2024-05-09 | 1 day | 100% | Studying ERD slides provided. Understanding the relationship between each entity.
Developing ERD Diagram | 2024-05-09 | 2024-05-10 | 1 day | 100% | Defining and deciding each entity's definition, relationship, cardinality, and attributes. Then creating physical and logical ERD.
ERD Implmentation | 2024-05-10 | 2024-05-11 | 1 day | 100% | Created all the necessary schemas, UDT, tables, and their respective columns. Attended group meeting.
Assigned Stored Procedure | 2024-05-11 | 2024-05-11 | 12 hours | 100% | Completed my assigned stored procedure which was ShowWorkflowSteps, load ModeOfInstruction, and load Instructor.
Setting up JDBC for my group | 2024-05-12 | 2024-05-12 | 2 hours | 100% | Sharing all the necessary JDBC files to run JDBC query execution. Attended group meeting.
Setting up PowerPoint Slides for my group | 2024-05-12 | 2024-05-12 | 1 hour | 100% | Creating PowerPoint Slides.
Recorded PowerPoint Presentation | 2024-05-16 | 2024-05-16 | 2 hours | 100% | Finished recording my powerpoint presentation video. Attended group meeting.
Final Project Submission | 2024-05-17 | 2024-05-17 | 2 hours | 20%
0%

## Jianhao Jin
To-do list
To be completed by: |  | 2024-05-15 |  | Name: Jianhao Jin
Deadline: |  | 2024-05-15 |  | Date: 5/17/24
Project 3
% done | Phase | Start By | Finish By | Number of Hour used | Number Of Days | Revision Notes
100% | Meeting | 2024-05-10 | 2024-05-10 | 1 hours
100% | Load_Class | 2024-05-11 | 2024-05-11 | 7 hours
100% | Query 3 | 2024-05-11 | 2024-05-14 | less than a hour
100% | ShowTableStatusRowCount | 2024-05-11 | 2024-05-11 | 1 hours
100% | Meeting | 2024-05-12 | 2024-05-12 | 1 hours
100% | Meeting | 2024-05-14 | 2024-05-14 | 1 hours
100% | Testing | 2024-05-14 | 2024-05-14 | less than a hour
100% | Recording | 2024-05-17 | 2024-05-17 | 1 hour
100% | Meeting | 2024-05-16 | 2024-05-16 | 1 hours
100% | Recording | 2024-05-17 | 2024-05-17 | 1 hour

## Jude Pierre
To-do list
To be completed by: |  |  |  | Name: Jude Pierre
Deadline: |  |  |  | Date: 5/17/24
Project 3
% done | Phase | Started On | Finished | Revised Due By | Number Of Days | Notes
100% | Design ERD | 2024-05-09 | 2024-05-10 |  | 1 | Assisted in the design of the ERD.
100% | Load_Class Procedure | 2024-05-11 | 2024-05-12 |  | 4 hrs
100% | Process.usp_TrackWorkFlow Procedure | 2024-05-10 | 2024-05-12 |  | 2
100% | Test query | 2024-05-15 | 2024-05-16 |  | 1 | Custom DB test query
100% | Powerpoint Presentation | 2024-05-14 | 2024-05-17 |  | 2 | Assisted in making the PowerPoint presentation.
100% | Gantt Chart | 2024-05-16 | 2024-05-16 |  | 2 hours
100% | Recording | 2024-05-17 | 2024-05-17 |  | 3 hours
100% | Presenting JDBC | 2024-05-17 | 2024-05-17 |  | 1 hour

## Jamal Siddiqui
To-do list
To be completed by: |  |  |  | Name: Jamal Siddiqui
Deadline: |  |  |  | Date: 5/17/24
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Initial Step | 2024-04-30 | 2024-05-01 |  | 2 Days | Contacted members of the group and made a server for us all to connect
100% | Reading Through Requirements | 2024-05-05 | 2024-05-05 |  | 1 Day
100% | Planning | 2024-05-06 | 2024-05-06 |  | 1 Day | The group leader split the work and gave everyone a choice
100% | Picking Sections of Work | 2024-05-10 | 2024-05-10 |  | 1 Day
100% | Stored Procedure - Load_BuildingLocation | 2024-05-12 | 2024-05-13 |  | 2 Days
100% | Drop Foreign Keys | 2024-05-13 | 2024-05-13 |  | 1 Day | This portion was finished by another member before I could start working on it, their function worked fine.
100% | Testing | 2024-05-13 | 2024-05-13 |  | 1 Day
100% | Hand-off | 2024-05-14 | 2024-05-14 |  | 1 Day
100% | Add to Presentation/Record | 2024-05-14 | 2024-05-14 |  | 1 Day

## Kathy He
To-do list
To be completed by: |  |  |  | Name: Kathy He
Deadline: |  |  |  | Date: 5/17/24
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Preparation | 2024-05-07 | 2024-05-08 |  | 1 day
100% | ERD Model Development | 2024-05-08 | 2024-05-10 |  | 2 days
100% | Meeting | 2024-05-10 | 2024-05-10 |  | 1 day
100% | Meeting | 2024-05-12 | 2024-05-12 |  | 1 day
100% | Query 1 for testing design | 2024-05-11 | 2024-05-14 |  | 3 days
100% | Query 2 for testing design | 2024-05-11 | 2024-05-14 |  | 3 days
100% | Query 3 for testing design | 2024-05-11 | 2024-05-14 |  | 3 days
100% | Query 4 for testing design | 2024-05-11 | 2024-05-14 |  | 3 days
100% | Query 5 for testing design | 2024-05-11 | 2024-05-14 |  | 3 days
100% | Query 6 for testing design | 2024-05-11 | 2024-05-14 |  | 3 days
100% | Query 7 for testing design | 2024-05-11 | 2024-05-14 |  | 3 days
100% | Query 8 for testing design | 2024-05-11 | 2024-05-14 |  | 3 days
100% | Meeting | 2024-05-14 | 2024-05-14 |  | 1 day
100% | Meeting | 2024-05-16 | 2024-05-16 |  | 1 day
100% | Process.TruncateWorkflowStepsTable | 2024-05-15 | 2024-05-15 |  | 1 day | Added to optimize displaying of workflow
100% | Adding Constraints to database | 2024-05-15 | 2024-05-17 |  | 2 days | Noticed some issues with old design and revamped database
100% | Transforming Derived columns | 2024-05-15 | 2024-05-17 |  | 2 days | Noticed some issues with old design and revamped database
100% | Adding new Default constraints | 2024-05-15 | 2024-05-17 |  | 2 days | Noticed some issues with old design and revamped database
0% | Recording | 2024-05-14 | 2024-05-15 |  | 1 day
100% | Recording | 2024-05-16 | 2024-05-15 | 2024-05-17 | 1 day | Deadline pushed back
0% | Editing | 2024-05-15 | 2024-05-15 |  | 5 hours
100% | Editing | 2024-05-17 | 2024-05-15 | 2024-05-17 | 5 hours | Deadline pushed back
0% | Submission | 2024-05-15 | 2024-05-15 |  | 1 hour
100% | Submission | 2024-05-17 | 2024-05-15 | 2024-05-17 | 1 hour | Deadline pushed back

## Osvaldo Talavera
To-do list
To be completed by: |  |  |  | Name: Osvaldo Talavera
Deadline: |  |  |  | Date: 5/17/24
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-05-08 | 2024-05-09 |  | 1 day
100% | Preparation (Reading through requirements) | 2024-05-09 | 2024-05-10 |  | 1 day
100% | Do Procedure Load_Department_Instructor | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2 days | This procedure required the Department Table and Instructor Table Procedures to be done.
100% | Do Procedure Load_Department | 2024-05-10 | 2024-05-11 |  | 1 day
100% | Do Procedure Load_QueensCourseSchedule | 2024-05-10 | 2024-05-13 | 2024-05-14 | 4 days
100% | Query: How many instructors are in each department? | 2024-05-12 | 2024-05-13 |  | 1 day
100% | Testing | 2024-05-11 | 2024-05-13 | 2024-05-15 | 4 days
100% | Attended Meetings 5/10, 5/12, 5/14/ 5/16 | 2024-05-10 | 2024-05-15 | 2024-05-17 | 5 Days | Talked with multiple group members on discrepancies or concerns about procedures or model
100% | Video Explaining my Procedures | 2015-05-15 | 2024-05-15 | 2024-05-17 |  | We got an extension
100% | Follow-up